## Sheet1
Risk_id | Risk_description | Likelyhood | Impact | Severity | Owner | Mitigation action
1 | Laptop might crash or get stolen | Low | High | High | Developer | Save the backup on the cloud or onedrive
2 | Delay in steps | Medium | High | High | Developer | Ensure the project plan is as accurate as possible. Use tracking board to track the progress
3 | Inadequate testing might lead to failure to perform app accordingly | High | High | High | Developer | Ensure the coverage report is 100%. Use automated testing for unit tests and integration tests
4 | Project budget may run out | Medium | High | High | Developer | Configure the VM with sufficient datasize and ensure to switch off VM after work.
5 | VM goes down | Low | Medium | Medium | Developer | Regularly push the source code to github
6 | Security attacks | Low | High | High | Developer | Do not send or revieve and sessitive information